## DistributedTeamsRiskFramework
Distributed Teams Risk Framework
Ian McDowall
Major Theme | Risk Theme | Risks | ID
Development approach and standards | Teams have differing approaches to software development | Differing definitions of when work is 'done' | 1.1.1
|  | Differing expectations around required quality of the final product | 1.1.2
|  | Different expectations around future maintainability and extensibility of code | 1.1.3
|  | Team members following different development methodologies and standards | 1.1.4
|  | Lack of agreement / unfamiliarity with code libraries | 1.1.5
|  | Unnecessary refactoring or rewriting of other teams code | 1.1.6
|  | Variations in testing, automation, and test-case coverage | 1.1.7
| Differences in how teams manage and measure software development | Incompatible techniques or metrics for estimating work packages and completion | 1.2.1
|  | Differences in measuring and reporting development velocity and overall progress | 1.2.2
|  | Differing approaches to overall development workflow | 1.2.3
| Teams have different approaches to delivering code | Differing deployment processes, tools, and post-deployment checks | 1.3.1
|  | Different expectations around documentation scope and coverage | 1.3.2
Tools and software | There are different development tools in use across the teams | Difference in development tools, repositories etc. | 2.1.1
|  | Incompatibly between tools | 2.1.2
|  | Governance and compliance overhead around tool use | 2.1.3
|  | A need for teams to learn new tools | 2.1.4
| There are problems with communication and knowledge sharing tools | Lack of common instant communication platform e.g. Messenger | 2.2.1
|  | Incompatible, poor quality or restricted video conferencing and screen sharing tools | 2.2.2
|  | Partial coverage or unsuitable knowledge sharing tools | 2.2.3
|  | Lack of, poor quality, or restricted document sharing repositories | 2.2.4
| Infrastructure and IT policy issues | Poor network connectivity between teams or individuals | 2.3.1
|  | Restrictive IT standards / policies driven by client or lead development party | 2.3.2
|  | Management overhead for teams and individuals e.g. multiple passwords | 2.3.3
Distance and time zone | Impact of team members spread across multiple time zones | Time difference makes scheduling calls / meetings difficult | 3.1.1
|  | Delay in responses to questions impacting time, cost and team motivation | 3.1.2
|  | Time difference delays / restricting communication with clients | 3.1.3
|  | Working across multiple time zones impacts team work life leading to fatigue and burn-out | 3.1.4
|  | Lack of support from parent organisation for staff working across different time zones | 3.1.5
| Impact of distance between team members | Problems getting key people together quickly to solve issues | 3.2.1
|  | Restricted ability to get people in one place for project kick-off, briefings etc. | 3.2.2
|  | Difficult to develop sense of 'one-team' when members haven't met | 3.2.3
|  | Calls with clients when teams are distributed makes it hard to present a 'unified' face | 3.2.4
|  | Staff on boarding is more difficult | 3.2.5
|  | Poor connectivity or call quality in some regions impacts team | 3.2.6
Culture and language | Country impact on working hours | Differing working days or times of working | 4.1.1
|  | Differing national holidays across the team | 4.1.2
|  | Religious festivals restricting working hours | 4.1.3
|  | Differing local employment laws and policies | 4.1.4
| Issues around multiple team languages | Teams working outside of their native languages | 4.2.1
|  | Lack of a common team language | 4.2.2
|  | Strong or unfamiliar accents impacts communication | 4.2.3
|  | Poor language skills leading to misunderstanding or reduced communication | 4.2.4
| Issues caused by differing cultural perspectives | National culture influences behaviour and attitudes | 4.3.1
|  | Assumptions are made based on individual's culture | 4.3.2
|  | Differing non-verbal communication and meaning | 4.3.3
|  | Attitudes to working outside of contracted hours | 4.3.4
|  | Differing approach to organisation hierarchies e.g. questioning decisions | 4.3.5
Team building and management | Problems building and maintaining a shared team culture | Lack of shared vision and sense of one team | 5.1.1
|  | Fear of change from some team members | 5.1.2
|  | Hard to asses if remote staff are working efficiently | 5.1.3
|  | Difficult to assess motivation and happiness of remote staff | 5.1.4
|  | Differing or conflicting parent company cultures across teams | 5.1.5
|  | Conflicts around where expertise sits in the team e.g. Java vs. AEM | 5.1.6
| Issues around management of remote teams | Leadership team is elsewhere / not involved | 5.2.1
|  | Project Manager is remote from team members | 5.2.2
|  | Lack of clarity around line-management | 5.2.3
|  | Reluctance to follow guidelines from other teams | 5.2.4
|  | Poor or non-existent holiday cover | 5.2.5
|  | Hard to ensure real involvement in remote calls | 5.2.6
Clients and their organisation | Client related issues | Client remote from main team | 6.1.1
|  | Client's other commitments makes communication slow | 6.1.2
|  | Client language or time zone issues | 6.1.3
|  | Difficulty building relationship with remote client | 6.1.4
|  | Harder to manage issues when client is remote | 6.1.5
|  | Regular face-to-face sessions can be hard or impossible | 6.1.6
| Client organisational issues | Complex organisational decision making process | 6.2.1
|  | Organisational culture may not support distributed working | 6.2.2
|  | Delays with steering committees or approvals | 6.2.3
|  | Lack of support from organisation's IT and security teams | 6.2.4
| Issues when client's provide development teams | Client development teams 'become our clients too' so are hard to manage even if less experienced | 6.3.1
|  | Client's organisational culture or approaches can affect development approach | 6.3.2
|  | Client teams feel their opinion should carry more weight | 6.3.3
|  | Client teams have internal escalation paths and ability to negatively promote the project | 6.3.4
Communication | Issues communicating scope at the start of the project | Time required to adequately brief the distributed team | 7.1.1
|  | Communicating all aspects of project and development approach | 7.1.2
|  | Ensuring full understanding of relevant project requirements | 7.1.3
| Issues with on-going communication | Communicating ongoing change | 7.2.1
|  | Communicating progress to the Project team | 7.2.2
|  | Team over-reliance on email communication | 7.2.3
|  | Regular communication of change to the developers | 7.2.4
|  | Communicating refined processes as the project matures | 7.2.5
| Problems with team member communication | Lack of face-to-face / social interaction builds weaker relationships between team members | 7.3.1
|  | Differing understanding of the client / project priorities across distributed teams | 7.3.2
|  | Need for increased documentation if teams don't work collaboratively | 7.3.3
Third party team members | Issues when not all team members are working for same company | Team conflicts of interest, especially when projects struggle | 8.1.1
|  | Split of responsibilities can be unclear or disputed | 8.1.2
|  | Lack of openness around issues or delays | 8.1.3
|  | Competition for future work | 8.1.4
|  | Finger pointing or blame deflection | 8.1.5
Financial and contractual | Financial risk to project | Need for increased management time | 9.1.1
|  | Timesheet approval across teams, especially third-party members | 9.1.2
|  | Billing and payment schedules if milestones missed | 9.1.3
|  | Payments to contractors | 9.1.4
|  | Financial mistrust between third-parties | 9.1.5
| Contractual risk | Flow-down of contracts | 9.2.1
|  | Cross border legal issues | 9.2.2
|  | Acceptability of use of third parties or contract staff | 9.2.3
| Confidentiality and information security risk | Maintaining information security / confidentiality | 9.3.1
|  | Sharing of client and project data between sites and parties | 9.3.2
|  | Cross border / organisation data transfer | 9.3.3
Project Management | Need for increased PM time | Increased complexity of team meetings | 10.1.1
|  | Additional communication overhead | 10.1.2
|  | Financial reconciliation time sheeting, reporting etc. | 10.1.3
| Complexity of managing distributed resources | Need to delegate to local PMs or leads | 10.2.1
|  | No direct contact with developers | 10.2.2
|  | Limited visibility into what other teams are doing | 10.2.3
|  | Complexity if PM is in a different location to teams | 10.2.4
|  | Complexity of managing staff not in same organisation | 10.2.5